## Overview
Iraje EPM — Project File Index
A guide to every file in this project, who needs it, and when.
Workbook tabs
Overview | You are here. Quick orientation + tab navigation.
Index | The big table. Every file, what it is for, who needs it, when. Filterable, sortable, color-coded.
Workflow | Timeline view. Which files matter at each phase from "blank VM" to "verified EPM".
Quick Reference | Copy-paste commands, default passwords, key paths, useful diagnostic snippets.
Category legend
Script | PowerShell entry points you actually run.
Module | PowerShell .psm1 files imported by the installer. Don't edit unless extending the framework.
Asset | Operator-staged files. Mostly from Iraje; one folder from the Windows ISO. The installer reads from here.
Documentation | Manuals, READMEs, this workbook.
Runtime | Generated by the installer or verifier at runtime. Not in your project folder.
Workbook | This index.xlsx itself.
How to use this workbook
1. Read the Overview tab (you are here).
2. Click "Index" to see every file. Use the auto-filter (top row) to narrow down by Category, Audience, or Required.
3. Click "Workflow" to see when each file matters during a fresh build.
4. Bookmark "Quick Reference" for copy-paste commands and default values.
5. The first column on each sheet is hyperlinked back to the Overview when applicable.
LAYOUT NOTE — auto-detect is on
The project is split into Scripts\, Manuals\, modules\, and assets\ subfolders.
Install-IrajeEPM.ps1 auto-detects the project root: if modules\ is not a sibling of the script, it walks one level up. This means both layouts work without changes:
- Flat layout: Install-IrajeEPM.ps1 + modules\ + assets\ all at the project root.
- Subfolder layout (current): Scripts\Install-IrajeEPM.ps1 with modules\ and assets\ one level up.
The same auto-detection applies to the default -AssetsRoot. You only need to pass -AssetsRoot explicitly if your assets folder lives somewhere unusual.
Test-IrajeEPM.ps1 is single-file with no module imports, so it works from anywhere unchanged.

## Index
Project File Index
# | Category | File / Folder | Type | Location | Description | Significance | Audience | When you need it | Required? | Source
1 | Script | Scripts\ | Folder | Project root | Container folder for the two PowerShell entry points. | Holds Install-IrajeEPM.ps1 and Test-IrajeEPM.ps1. The installer auto-detects the project root by walking one level up if modules\ is not a sibling, so this layout works out of the box. | Operator | Step 13 (when copying project to VMs) | Required | Bundled
2 | Script | Install-IrajeEPM.ps1 | PowerShell .ps1 | Scripts\ | The one-click installer entry point. Drives the entire 44-step EPM build (or 7-step NTP build). | Run this once per server. Hardens the Windows Server, installs AD, RDS, IIS, MySQL, deploys the EPM app, applies GPOs. Reboot-survivable via a SYSTEM scheduled task. Idempotent: safe to re-run after any failure. | Ops engineer running the install | Step 21 (NTP install), Step 22 (EPM install) | Required | Bundled
3 | Script | Test-IrajeEPM.ps1 | PowerShell .ps1 | Scripts\ | Read-only verifier. Confirms every change made by the installer is still in place. Generates a color-coded HTML report. | Run any time, on either server. Auto-detects the role and runs the appropriate battery (7 NTP checks or 60+ EPM checks). Exits 0 on PASS, 1 on FAIL. Safe during production traffic. | Ops engineer / SRE / change auditor | After install, then periodically as drift detector | Required | Bundled
4 | Module | modules\IrajeEPM.Core.psm1 | PowerShell module | modules\ | Shared primitives: logging, state machine, OS detection, elevation, reboot/resume scheduled task, native command wrapper. | Imported by both installer modules and the entry-point script. Manages C:\ProgramData\IrajeEPM\state.json and logs to C:\ProgramData\IrajeEPM\logs\. You should never edit this unless you are extending the framework itself. | Framework maintainer (rarely opened by operator) | Auto-loaded at every installer run | Required | Bundled
5 | Module | modules\IrajeEPM.NTP.psm1 | PowerShell module | modules\ | Phase 1 — NTP server-side step functions (7 idempotent steps). | Configures w32time as a reliable NTP source (AnnounceFlags=5, NtpServer Enabled, UDP/123 firewall rule). Only invoked when -Role NTPServer is passed. | Framework maintainer | Auto-loaded when running on the NTP server | Required | Bundled
6 | Module | modules\IrajeEPM.EPMServer.psm1 | PowerShell module | modules\ | Phases 2-17 — the bulk of the install: AD, RDS, IIS, MySQL, Flyway, GPOs, Myrtille, Shadow RemoteApp, IIS warm-up. | 44 idempotent step functions wired into an orchestrator. Triggers the two mandatory reboots (DC promotion, RDS install). Anything you need to change about the install logic lives here. | Framework maintainer | Auto-loaded when running on the EPM server | Required | Bundled
7 | Asset | assets\ | Folder | Project root | Root of the operator-provided payload. Empty by default; you populate it before launching the installer. | The installer validates this folder layout at startup and refuses to run if anything is missing. Sibling of Install-IrajeEPM.ps1. | Operator (you must stage this) | Step 15-18 (before any install) | Required | You create
8 | Asset | assets\EPM_Setup_files_V1\ | Folder | assets\ | The Iraje vendor payload root. Treat as opaque — Iraje ships this. | Contains the 7-Zip-protected tools archive, the application bits (EPMDashboard, IrajeWorker, IrajeSecureAccess), and the GPO backups. | Operator | Step 16 — before running the installer | Required | From Iraje
9 | Asset | EPM_Tools_Setup.7z | 7-Zip archive | assets\EPM_Setup_files_V1\ | Password-protected bundle of dependency installers (Chrome, .NET hosting, OTP/Erlang, RabbitMQ, MySQL, MySQL Workbench, vc_redist). | Extracted by the installer (Phase 9) using the password you pass via -ArchivePassword. Without this, none of the runtime dependencies install. Ask Iraje for the password under separate cover. | Operator | Step 16 — placed before install | Required | From Iraje
10 | Asset | EPM_App_Setup_Configuration\EPMDashboard\ | Folder | assets\EPM_Setup_files_V1\EPM_App_Setup_Configuration\ | IIS web application bits. Copied to C:\Windows\Web\IrajeEPM\EPMDashboard\ during install. | This is the actual EPM dashboard web app the user interacts with. Hosted under the EPMDashboard IIS site on HTTPS. | Operator (just stage it) | Step 16 | Required | From Iraje
11 | Asset | EPM_App_Setup_Configuration\EPMMessageService\ | Folder | assets\EPM_Setup_files_V1\EPM_App_Setup_Configuration\ | Worker service binaries. Copied to C:\Windows\Web\IrajeEPM\IrajeWorker\. | Becomes the iworker Windows service. EpmWorker.exe inside this folder is the binary the service points at; if missing, the service will not start. | Operator | Step 16 | Required | From Iraje
12 | Asset | EPM_App_Setup_Configuration\IrajeSecureAccess\ | Folder | assets\EPM_Setup_files_V1\EPM_App_Setup_Configuration\ | Myrtille browser-RDP gateway bits. | Provides browser-based RDP via three vendor PowerShell installers (Web, Admin Services, Services). Phase 13 of the install. | Operator | Step 16 | Required | From Iraje
13 | Asset | EPM_App_Setup_Configuration\software\ | Folder | assets\EPM_Setup_files_V1\EPM_App_Setup_Configuration\ | Copied verbatim to C:\software\ on the EPM server. | Whatever Iraje puts here ends up at C:\software\. Often utility scripts, runbooks, or operator tools. | Operator | Step 16 | Required | From Iraje
14 | Asset | EPM_App_Setup_Configuration\web\ | Folder | assets\EPM_Setup_files_V1\EPM_App_Setup_Configuration\ | Copied verbatim to C:\Windows\Web\. Contains Shadow.exe, PsExec.exe. | Shadow.exe is published as a RemoteApp on the EPM App session collection. PsExec.exe is used during runtime for remote command execution. | Operator | Step 16 | Required | From Iraje
15 | Asset | EPM_App_Setup_Configuration\epm-db\ | Folder (SQL migrations) | assets\EPM_Setup_files_V1\EPM_App_Setup_Configuration\ | Flyway SQL migration files for the epm database. | Applied by flyway migrate during Phase 11. Defines the entire epm database schema. | Operator | Step 16 | Required | From Iraje
16 | Asset | flyway-commandline-11.20.2.zip | ZIP archive | assets\EPM_Setup_files_V1\EPM_App_Setup_Configuration\ | The Flyway CLI. Extracted to C:\flyway-11.20.2\ during install. | Adds C:\flyway-11.20.2 to the machine PATH and sets FLYWAY_DB_USER / FLYWAY_DB_PASSWORD environment variables. | Operator | Step 16 | Required | From Iraje
17 | Asset | mysql-connector-j-9.x.x.jar | JAR | assets\EPM_Setup_files_V1\EPM_App_Setup_Configuration\ | MySQL JDBC driver. Placed in C:\flyway-11.20.2\drivers\. | Without this, Flyway cannot connect to MySQL. Filename version varies by Iraje delivery. | Operator | Step 16 | Required | From Iraje
18 | Asset | db_setup.ps1 | PowerShell .ps1 | assets\EPM_Setup_files_V1\EPM_App_Setup_Configuration\ | Vendor post-install script. Invoked by the installer in Phase 12. | Reads $env:IRAJE_APPPOOL and $env:IRAJE_DBPASSWORD which the installer sets. If the Iraje copy uses hard-coded $appPoolName / $dbPassword, you must edit the top to read from those env vars instead. | Operator (one-time edit) | Step 16 (edit before staging) | Required | From Iraje
19 | Asset | GPO\EPM_DDP_v1.0\ | GPO backup folder | assets\EPM_Setup_files_V1\GPO\ | Default Domain Policy backup. Imported into the existing Default Domain Policy during Phase 10. | Must contain manifest.xml + a {GUID}-named subfolder. Without it, the Default Domain Policy is left unchanged (insecure default). | Operator | Step 16 | Required | From Iraje
20 | Asset | GPO\EPM_nologoff_v1.0\ | GPO backup folder | assets\EPM_Setup_files_V1\GPO\ | Policy applied to the Nologoff OU. | Linked to OU=Nologoff and used for user accounts that should never log off (the irajejobs service account, etc.). | Operator | Step 16 | Required | From Iraje
21 | Asset | GPO\EPM_winupdate_v1.0\ | GPO backup folder | assets\EPM_Setup_files_V1\GPO\ | Policy applied to the Winupdate OU. | Controls Windows Update behavior for the winupdate service account. | Operator | Step 16 | Required | From Iraje
22 | Asset | GPO\EPM_Iraje_v1.0\ | GPO backup folder | assets\EPM_Setup_files_V1\GPO\ | Policy applied to the Iraje OU (optional — if Iraje provides it). | If absent, the installer warns and skips the Iraje OU GPO link. Not strictly required but recommended. | Operator | Step 16 | Optional | From Iraje
23 | Asset | assets\sxs\ | Folder (.cab files) | assets\ | .NET 3.5 source files copied from the Windows Server ISO. | Windows Server does not ship .NET 3.5 enabled. The installer needs source files (~80 MB of .cab files) from the ISO at \sources\sxs\. Mount the ISO and copy this folder over. | Operator | Step 17 | Required | From Windows ISO
24 | Documentation | Manuals\ | Folder | Project root | Container folder for all human-readable manuals. | Holds the four Word docs. Open any of them with Word, LibreOffice, or Google Docs. Drop in any future doc here too. | Anyone | Anytime | Required | Bundled
25 | Documentation | GETTING-STARTED.docx | Word doc | Manuals\ | 0-to-100 onboarding manual. Walks an absolute beginner from "I have nothing" through verified EPM. | Start here if you have never built a Windows Server VM before. 7 parts, 33 sections, 3 appendices: VM creation, asset staging, install, verify, troubleshooting. | Beginner doing first install | Read once, before you start | Required reading | Bundled
26 | Documentation | INSTRUCTIONS.docx | Word doc | Manuals\ | Operator manual specifically for Install-IrajeEPM.ps1. | Targets ops engineers comfortable with Windows Server. Covers asset prep, parameter reference, step-by-step run, reboot expectations, recovery. | Ops engineer with prior server experience | Read once, before first install | Required reading | Bundled
27 | Documentation | INSTRUCTIONS-TestIrajeEPM.docx | Word doc | Manuals\ | Operator manual specifically for the verifier script Test-IrajeEPM.ps1. | Standalone manual for the verifier. 13 sections covering parameters, output anatomy, every single check, troubleshooting, FAQ. Read it before integrating the verifier into a monitoring pipeline. | Anyone running the verifier | Before first verify run | Required reading | Bundled
28 | Documentation | README.docx | Word doc | Manuals\ | Quick reference card. The "I know what I am doing, just remind me" doc. | Parameter tables, usage examples, post-install verification checklist. Print this and tape it to the wall. | Experienced operator who needs a refresher | Any time you need a quick lookup | Optional | Bundled
29 | Workbook | index.xlsx | Excel workbook | Project root | This file. Navigable index of every file in the project, with workflow and quick-reference tabs. | Use this as your single source of truth for "what is this file and do I need it". Filter by Category, Source, or Required. | Anyone new to the project | Any time you need to orient yourself | Required reading | Bundled
30 | Runtime | C:\ProgramData\IrajeEPM\state.json | JSON | On each server (auto-created) | Step-by-step state of an in-progress installer. Survives reboots. | Stores the Role, the Params hashtable, and every step name with its status (Pending / InProgress / Done / Failed / Skipped). Edit a Done -> Pending to force a single step to re-run on next install. Delete the file to start completely fresh. | Operator (during troubleshooting) | After first install starts | Auto | Auto-generated
31 | Runtime | C:\ProgramData\IrajeEPM\logs\install-*.log | Text transcript | On each server (auto-created) | Full PowerShell transcript of every installer run. One file per launch. | Capture everything the installer printed: each [STEP] line, [OK] / [WARN] / [ERROR] events, full stack traces on failure. First place to look when something goes wrong. | Anyone debugging an install failure | Generated during install | Auto | Auto-generated
32 | Runtime | C:\ProgramData\IrajeEPM\verify\report-*.html | HTML report | On each server (auto-created) | Color-coded HTML report from each verifier run. Self-contained (no external CSS). | Email it, attach to tickets, archive for compliance. Each Pass/Fail/Warn is a colored card with detail and remediation. Survives across reboots; archive periodically. | Anyone reviewing health (operator, SRE, audit) | Generated by every Test-IrajeEPM.ps1 run | Auto | Auto-generated
33 | Runtime | Scheduled Task: IrajeEPMResume | Windows Scheduled Task | Task Scheduler (auto-created) | SYSTEM-context task that re-launches Install-IrajeEPM.ps1 after each reboot. | Created before each reboot-triggering step. Auto-deleted on successful completion. If you see this task still registered after the installer finished, the run did not complete — investigate. | Operator (visible in Task Scheduler) | Exists during install, removed on success | Auto | Auto-generated
34 | Runtime | 7-Zip (7z.exe) | Windows installer | C:\Program Files\7-Zip\ | Free archiver. Installed manually on the EPM server before launching the installer. | Required to extract the password-protected EPM_Tools_Setup.7z. Download from 7-zip.org and install with defaults. Without it, Phase 9 of the install fails. | Operator | Before first EPM install run | Required | You install

## Workflow
Workflow — what to use at each phase
Phase | Step | What you do | Files involved | Approx. time
Phase 1 — Procure | 1 | Choose a hypervisor (VMware Workstation, Hyper-V, VirtualBox). Install it. | — | 15-30 min
Phase 1 — Procure | 2 | Download a Windows Server ISO (Microsoft Evaluation Center or licensed). | — | 20-60 min (download)
Phase 1 — Procure | 3 | Receive the EPM patch from Iraje (EPM_Setup_files_V1 + 7z password + GPO backups). | EPM_Setup_files_V1\ | Varies (vendor)
Phase 2 — VM build | 4 | Create the NTP server VM (2 vCPU, 2GB RAM, 40GB disk). | — | 5 min
Phase 2 — VM build | 5 | Create the EPM server VM (4 vCPU, 8GB RAM, 80GB disk). | — | 5 min
Phase 2 — VM build | 6 | Install Windows Server on each VM. Same ISO works for both. | — | 20 min per VM
Phase 3 — VM prep | 7 | Set static IP, time zone, point DNS at self (EPM server), keep in workgroup. | — | 5 min per VM
Phase 3 — VM prep | 8 | Take a "Clean install" snapshot of each VM. | — | 1 min per VM
Phase 4 — Stage assets | 9 | Place EPM_Setup_files_V1 contents in assets\ folder. | assets\EPM_Setup_files_V1\ | 5 min
Phase 4 — Stage assets | 10 | Copy Windows ISO\sources\sxs\ to assets\sxs\. | assets\sxs\ | 2 min
Phase 4 — Stage assets | 11 | Edit db_setup.ps1 to read from env vars instead of hard-coded password. | db_setup.ps1 | 2 min (one-time)
Phase 4 — Stage assets | 12 | Validate the assets layout (Test-Path each required folder). | assets\* | 1 min
Phase 5 — Copy to VMs | 13 | Copy the entire project folder to each VM at C:\IrajeEPMTools\ (preserve the Scripts\, modules\, assets\, Manuals\ subfolders). | Scripts\, modules\, assets\, Manuals\ | 5 min
Phase 5 — Copy to VMs | 14 | Install 7-Zip on the EPM server (download from 7-zip.org). | 7-Zip | 1 min
Phase 6 — Install NTP | 15 | On NTP server: Set-ExecutionPolicy Bypass; cd C:\IrajeEPMTools\Scripts; .\Install-IrajeEPM.ps1 -Role NTPServer. | Scripts\Install-IrajeEPM.ps1 | 30 sec
Phase 6 — Install NTP | 16 | Verify NTP install passed (.\Test-IrajeEPM.ps1 -Role NTPServer). | Scripts\Test-IrajeEPM.ps1 | 15 sec
Phase 7 — Install EPM | 17 | On EPM server: cd C:\IrajeEPMTools\Scripts; launch installer with all parameters. Walk away. | Scripts\Install-IrajeEPM.ps1 | 30-60 min
Phase 7 — Install EPM | 18 | Server reboots after DC promotion. Auto-resumes via scheduled task. | state.json, IrajeEPMResume task | Automatic
Phase 7 — Install EPM | 19 | Server reboots after RDS roles install. Auto-resumes. | state.json, IrajeEPMResume task | Automatic
Phase 7 — Install EPM | 20 | Installer prints "EPM server box-making finished successfully." in green. | — | End of run
Phase 8 — Verify | 21 | On EPM server: cd C:\IrajeEPMTools\Scripts; .\Test-IrajeEPM.ps1 with all parameters. | Scripts\Test-IrajeEPM.ps1 | 15-45 sec
Phase 8 — Verify | 22 | Open the HTML report in a browser. Confirm overall verdict is PASS. | verify\report-*.html | 2 min
Phase 8 — Verify | 23 | Browser smoke test: navigate to https://<EPM-IP>/ and log in as iEPM. | — | 2 min
Phase 8 — Verify | 24 | Snapshot both VMs as "EPM installed and verified". | — | 1 min per VM

## Quick Reference
Quick Reference — commands, paths, defaults
Default values (override on the command line if needed)
Key | Value | Notes
Default user password placeholder | Default$User2026! | You must change this. AD complexity rules apply.
DSRM password | @@Re$tore@!2323@@ | Directory Services Restore Mode
iEPM admin password | Enc$rypt@012026 | For the iEPM AD admin user
MySQL root password | @@Fzcv##2026@@ | For the MySQL Server install
HTTPS port | 443 | Override with -HttpsPort
Domain TLD | .local | Must end in .local
Forest functional level | WinThreshold (2016) | Or higher
Key paths
Key | Value | Notes
Project folder (recommended) | C:\IrajeEPMTools\ | Local; not on network share
Scripts folder | C:\IrajeEPMTools\Scripts\ | Contains Install-IrajeEPM.ps1 + Test-IrajeEPM.ps1
Manuals folder | C:\IrajeEPMTools\Manuals\ | All Word doc manuals
Modules folder | C:\IrajeEPMTools\modules\ | 3 .psm1 files imported by the installer
Assets folder | C:\IrajeEPMTools\assets\ | Operator-staged Iraje payload + SxS
Install state file | C:\ProgramData\IrajeEPM\state.json | Auto-managed by installer
Install logs | C:\ProgramData\IrajeEPM\logs\ | One file per install run
Verify HTML reports | C:\ProgramData\IrajeEPM\verify\ | One file per verify run
EPM app root | C:\Windows\Web\IrajeEPM\ | Installer creates this
IIS dashboard files | C:\Windows\Web\IrajeEPM\EPMDashboard\ | From assets EPMDashboard
Worker service binaries | C:\Windows\Web\IrajeEPM\IrajeWorker\ | Holds EpmWorker.exe
Myrtille install root | C:\Windows\Web\IrajeEPM\IrajeSecureAccess\ | Browser RDP
Flyway CLI | C:\flyway-11.20.2\flyway.cmd | Added to machine PATH
Flyway drivers | C:\flyway-11.20.2\drivers\ | MySQL connector JAR here
Software dump | C:\software\ | From assets software
Resume scheduled task | IrajeEPMResume | Auto-deleted on success
Network ports
Key | Value | Notes
NTP server | UDP 123 inbound | Firewall rule: "NTP Server UDP 123"
EPM HTTPS | TCP 443 inbound | IIS EPMDashboard site
SMB | TCP 445 inbound | For domain workstations
RDP | TCP 3389 inbound | Plus -CustomRdpPort if you remap
MySQL | TCP 3306 (local) | Server only, not exposed
MySQL X | TCP 33060 (local) | Server only, not exposed
Commands you will type
Open elevated PowerShell | Right-click Start -> "Windows PowerShell (Admin)" (Title bar must say "Administrator")
Allow scripts for the session | Set-ExecutionPolicy -Scope Process -ExecutionPolicy Bypass -Force
Change directory to the Scripts folder | cd C:\IrajeEPMTools\Scripts
Install NTP server | .\Install-IrajeEPM.ps1 -Role NTPServer
Install EPM server (substitute YOUR values) | .\Install-IrajeEPM.ps1 ` -Role EPMServer ` -DomainName 'Iepm.local' ` -ServerIP '192.168.1.50' ` -NtpServerIP '192.168.1.81' ` -ArchivePassword '<7z-pwd>' ` -DefaultUserPassword 'Default$User2026!'
Verify NTP server | .\Test-IrajeEPM.ps1 -Role NTPServer
Verify EPM server | .\Test-IrajeEPM.ps1 ` -Role EPMServer ` -DomainName Iepm.local ` -ServerIP 192.168.1.50 ` -NtpServerIP 192.168.1.81 ` -MySqlRootPassword '@@Fzcv##2026@@'
Tail the latest install log | Get-ChildItem C:\ProgramData\IrajeEPM\logs\ ¦ Sort-Object LastWriteTime -Descending ¦ Select-Object -First 1 ¦ Get-Content -Wait -Tail 50
Force a clean re-run (delete state + resume task) | Unregister-ScheduledTask -TaskName IrajeEPMResume -Confirm:$false Remove-Item C:\ProgramData\IrajeEPM\state.json -Force
Re-set DNS to point at self (EPM box, post-DCpromo) | $iface = (Get-NetAdapter ¦ Where-Object Status -eq 'Up')[0].Name Set-DnsClientServerAddress -InterfaceAlias $iface -ServerAddresses 192.168.1.50,8.8.8.8
Restart the worker service | Restart-Service iworker
Recycle the dashboard app pool | Import-Module WebAdministration; Restart-WebAppPool EPMDashboard
Diagnostic snippets
Is this server a Domain Controller? | (Get-CimInstance Win32_OperatingSystem).ProductType # 2 = yes, DC
Is this server in a workgroup? | (Get-CimInstance Win32_ComputerSystem).PartOfDomain # False = workgroup
NTP source + last sync | w32tm /query /source; w32tm /query /status
Is the resume task gone (clean finish)? | Get-ScheduledTask IrajeEPMResume -ErrorAction SilentlyContinue # empty = good
Are all roles installed? | Get-WindowsFeature AD-Domain-Services, RDS-RD-Server, RDS-Web-Access, RDS-Gateway, RDS-Licensing, Web-Server, Web-WebSockets, Web-AppInit, NET-Framework-Core ¦ Select Name, Installed
iworker + RabbitMQ + MySQL service status | Get-Service iworker, RabbitMQ, MySQL* ¦ Format-Table Name, Status, StartType
IIS EPMDashboard site + app pool | Import-Module WebAdministration; Get-Website EPMDashboard; Get-Item 'IIS:\AppPools\EPMDashboard' ¦ Select name, state, managedRuntimeVersion, enable32BitAppOnWin64, startMode
Flyway info (from epmdms folder) | Set-Location 'C:\Windows\Web\IrajeEPM\epmdms'; flyway info